## Sheet1
Week 6 – Assignment #6 (Relaxing Travel - Part #2) Risk Register for Office Relocation Group 11 Pierce College – Session 6 2023 MIS 302: Project Management Professor: Joanne Brogden Document Created By: Kelli Penrose Date: 8/9/2023
Project Name: Office Relocation
ID No. | Risk | Description | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
1 | Contracted Employee Leaving The Project | Contracted Employee leaves the project due to unforeseen circumstance | Family emergency | Death or Illness | Prepare backup and shift task to another team member | Project Manager | High | High | Occurred and Handled
2 | Late Delivery Of IT & Office Equipment | Equipment delivered later than expected | Inclement weather | High Winds | Reschedule delivery for as soon as poosible | Project Manager | Low | High
3 | Misconfiguration Of Sabre Software | Firewall accidentally disabled during installation | Rushing during installtion | delayed equipment delivery | Double Check installation by another team member | IT Networking Professional | Low | Medium
4 | IT Equipment & Internet Installation Issues | Wifi connection weak | Poor Signal | Equipment to far from router | Purchase and install Wifi extenders | IT Networking Professional | Low | Low