## Sheet1
Requirement No. | Project objective | Business Need, Justification | Name | Category | Source | Status
1.0 Hardware | To move the 2nd location to fully virtual Travel agency
|  | Backup for 1st location | Justin & Elena | IT
1.1 Desktop |  | -To be moved to the 1st location |  |  | -2nd location | In progress
1.2 Laptops (6) |  | -Purchase order placed |  |  | -Office Depot | In progress
1.3 Printers (6) |  | -Purchase order place |  |  | -Amazon.com | In progress
2.0 Software | To move the 2nd location to fully virtual Travel agency | Sabre Travel Network software annual subscription for remote work | Justin & Elena | IT | -TPG & Silver Lake | In progress
2.1 Sabre | Airline bookings, car rentals, hotel reservations | Required for travel operations | Justin & Elena | IT | -TPG & Silver Lake | In progress
3.0 Services | To move the 2nd location to fully virtual Travel agency | To be configured & setup on laptops & printers for remote work | Jameer & Felicia | Networking | -PMA | In progress
3.1 Networking | Remote work and internet connection | Laptops, and online sales | Jameer & Felicia | Networking | -PMA | In progress
4.0 Office Equipment | To move the 2nd location to fully virtual Travel agency | 2nd location’s tables, chairs to home offices | Wyatt & Dylan | Equipment Moving | -2nd location | In Progress
5.0 Transportation | To move the 2nd location to fully virtual Travel agency | U-Haul rental to pack & move table, chairs, desktops to multiple destinations | Wyatt & Dylan | Transportation | -2nd location | In Progress
5.1 Rental | To relocate office furniture to home offices | Huge sized furniture need U-Haul Truck | Wyatt & Dylan | Transportation | -2nd location | In progress
6.0 Time: 4 weeks | To move the 2nd location to fully virtual Travel agency | Enforces the schedule of four weeks: Begin date 7/17/23 & | Elena | Business admin | 2nd location | In Progress
6.1 Begin date 7/17/23 | Moving operations start | Schdule implemetation and timely performance | Elena | Business admin | 2nd location | In progress
6.2 End date 8/16/23 | Timely operations | Ontime performance | Elena | Business admin | 2nd location | In progress
7.0 Budget of $50,000 | To move the 2nd location to fully virtual Travel agency | Total cost of moving, equipment purchase, transportation, & pay | Marie & Joseph | Top Management | 1st location | In progress
8.0 Cost | To move the 2nd location to fully virtual Travel agency | The total does not need to exceed $50,000 | Marie & Joseph | Project Management | 1st location | In progress
8.1 Cost Breakdown
8.1.1 Laptops | Remote work and internet connection | 6 x $1,000= $6,000 | Justin & Elena | Procurement | Office Depot | In progress
8.1.2 Printers | Home offices | 6 x $1000 = $6,000 | Justin & Elena | Procurement | Amazon | In progress
8.1.3 Software (Sabre) | Bookings and reservations | $10,000 | Justin & Elena | Procurement | TPG & Silver Lake | In progress
8.1.4 Rental | Office furniture transportation | $7,600 | Wyatt & Dylan | Transportation | U-Haul | In progress
8.1.5 Wage | Network professionals | $40/hr x 2 x 160 =12800 | PM: Morrese Morrison |  | PMA | In progress
| Equipment moving staff | $30/hr x 2 x 160 =9600
Total cost = $50,000 |  | Total cost = $50,000 | PM: Morrese Morrison
Week 3 - Assignment # 3 (Relaxing Travel Case Study - Requirements Traceability Matrix)
Group 11
Peirce College - Session 6
MIS 302 - Project Managment
Professor: Joanne Brogden
Document Created by: Jilalo Sherif
Date 7/20/2023